## Cover Page
AI Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  | 2024-08-07
Project Team Name |  | Insomniac
Project Topic |  | Facial age estimation
Task |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  | W2 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4 |  |  |  |  | W5 |  |  |  |  | W6
[8 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34
[8 empty] | 2024-07-14 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-22 | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-07-28 | 2024-07-29 | 2024-07-30 | 2024-07-31 | 2024-08-01 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-05 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | 2024-08-11 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16
1. Data Acquisition |  |  | 2024-07-14 | 2024-07-23 |  |  | Done | bar: 2024-07-14 to 2024-07-23
| 1.1. Data selection | Get data image for training model | 2024-07-14 | 2024-07-16 |  |  | Done | bar: 2024-07-14 to 2024-07-16
| 1.2. Data visualization | Visualization for a overall look at data | 2024-07-17 | 2024-07-20 |  |  | Done | bar: 2024-07-17 to 2024-07-20
| 1.3. Data preprocessing | Normalization and augmentation data | 2024-07-21 | 2024-07-23 |  |  | Done | bar: 2024-07-21 to 2024-07-23
2. Design model |  |  | 2024-07-23 | 2024-07-30 |  |  | Done | bar: 2024-07-23 to 2024-07-30
| 2.1. Choose the CNN architecture | Decided which model architecture will be used in project | 2024-07-23 |  |  |  | Done | bar: 2024-07-23
| 2.2. Implement in code | Implement idea using python and torch framework | 2024-07-24 | 2024-07-30 |  |  | Done | bar: 2024-07-24 to 2024-07-30
3. Training model |  |  | 2024-07-24 | 2024-08-14 |  |  | Done | bar: 2024-07-24 to 2024-08-14
| 3.1. Implement in code | Implement idea using python and torch framework | 2024-07-24 | 2024-07-30 |  |  | Done | bar: 2024-07-24 to 2024-07-30
| 3.2. Tuning hyperparameter | Setup initial parameter for the first training | 2024-07-30 |  |  |  | Done | bar: 2024-07-30
| 3.3. Training and validation | Training with GPU and debug | 2024-07-30 | 2024-08-14 |  |  | Done | bar: 2024-07-30 to 2024-08-14
4. Testing and improvement |  |  | 2024-08-01 | 2024-08-14 |  |  | Done | bar: 2024-08-01 to 2024-08-14
| 4.1. Adjusting the hyperparamenter | Change some parameter in the code | 2024-08-01 | 2024-08-14 |  |  | Done | bar: 2024-08-01 to 2024-08-04
| 4.2. Training again | Training with new change | 2024-08-01 | 2024-08-14 |  |  | Done | bar: 2024-08-02 to 2024-08-14
| 4.3. Compare the result | Compare the diffent of old and new model for the best model | 2024-08-02 | 2024-08-14 |  |  | Done | bar: 2024-08-02 to 2024-08-14
5. Creating user interface |  | Deployment model in webapp | 2024-08-02 | 2024-08-14 |  |  | Done | bar: 2024-08-02 to 2024-08-14
6. Writing report |  | Writing reports and the presentation slide using Power Point | 2024-07-30 | 2024-08-14 |  |  | Done | bar: 2024-07-30 to 2024-08-14